## Guidance Notes
Stakeholder Engagement Plan
This template has been produced by the Diocese of Bristol as part of its Project Planning Guide
Use this spreadsheet to consider who the main stakeholders are for your project and how you may need to engage with them.
1 | Begin by considering which model of Stakeholder Engagement Planning will work best for your context, two templates are included here.
2 | Review the Stakeholder Analysis Example as you will need to be aware of this as you consider the stakeholders in your project.
3 | Enter the PROJECT TITLE to the top of the Spreadsheet of your chosen template.
4 | Identify the title for the STAKEHOLDERS group.
This could be: PCC members or External organisations.
6 | Idneitfy who the STAKEHOLDER is.
This could be: PCC Treasurer or Neighbourhood Policing Team.
8 | Identify the INTEREST level for that stakeholder - how interested are they in your project and its outputs?
9 | Identify the INFLUENCE level for that stakeholder - how much influence over your project do they have?
10 | These two ratings will automatically then display the ACTION or aproach to engagement that should be taken with that stakeholder.
11 | Identify the BENEFITS or DISBENEFITS of the project that will be experienced by each stakeholder.
12 | Detail what your ENGAGEMENT STRATEGY will be for that stakeholder.
13 | Identify WHO is responsible for that engagement.
14 | Enter a Red, Red/Amber, Amber/Green or Green rating for how on track the engagement with that stakeholder is.
15 | In the Stakeholder Engagement Grip you can also highlight where you feel each stakeholder is in relation to the project: Anti, Sceptic, Neutral, Helpful or Champion
Sheets within this spreadsheet have been ‘Protected’ to restrict the accidental damaging of formulas and formatting within the template.
The password to unlock this is ‘1234’. (Click 'Review', then 'Unprotect Sheet')
Please do feel free to adjust the template as necessary to meet the needs of your project.

## Stakeholder Analysis Example
Interest | Influence
H | H | Collaborative/Empower |  | Stakeholder Analysis Grid
H | L | Consult
L | H | Involve and Consult | High | Consult | Engage | Engage | Engage/ Partner | Partner
L | L | Inform | INFLUENCE | Consult | Engage | Engage | Engage | Engage
H | M | Consult/Collaborate and empower |  | Consult | Consult | Engage | Engage | Engage
L | M | Inform/Involve and Consult |  | Inform | Inform | Consult | Engage | Engage
M | H | Involve and Consult/Collaborate and Empower | Low | Inform | Inform | Consult | Consult | Consult
M | L | Inform/Consult
M | M | Discretion |  | High | INTEREST |  |  | Low
R | H |  |  | To partner: | to work alongside
A/R | M |  |  | To engage: | to ask for input
A/G | L |  |  | To consult: | to ask for an opinion
G |  |  |  | To inform: | to keep up to date

## Stakeholder Engagement Grid
Stakeholder Map
Project title here
Use this form to consider the position of the key stakeholders in your project
Stakeholder | Role | Interest | Influence | Benefits or Disbenefits | Anti | Sceptic | Neutral | Helpful | Champion | RAG | Action (auto-completes) | Who is responsible for the action/engagement | Engagement Strategy
Stakeholder group title
Stakeholder 1 | Leader | H | L | Increased workload |  |  |  | x |  | A/R | Consult | ABC | Meet and discuss
Stakeholder 2 | Assistant | M | M | New opportunities |  |  |  |  | x | G | Discretion | DEF | Send a regular email update
Stakeholder group title (2)
Stakeholder 1
Stakeholder 2

## Stakeholder Engagement List
Stakeholder Engagement Plan
Project title here
Stakeholder | Status | Interest | Influence | Action
Stakeholder group title
Stakeholder 1 | A/R | H | L | Consult
Benefits: Disbenefits: Increased workload |  | Responsible for engagement: |  | ABC
Engagement Strategy: Meet with them 121 for regualr update meetings
Stakeholder 2 | G | M | M | Discretion
Benefits: New opportunities Disbenefits: |  | Responsible for engagement: |  | DEF
Engagement Strategy: Send a regular email update
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy:
Benefits: Disbenefits: |  | Responsible for engagement:
Engagement Strategy: