## Guidance Notes
Project Tracker
This template has been produced by the Diocese of Bristol as part of its Project Planning Guide
Use this spreadsheet to record any issues, changes, learning or dependencies that are part of your project or that arise through the lifespan of your project.
Issues Log
Issues are generally risks which have occurred and are impacting the project.
1 | Enter the PROJECT TITLE to the top of the Spreadsheet.
2 | DESCRIBE the issue that has arisen.
3 | Explain the IMPACT of the issue on the project.
4 | Idenfity who is the OWNER of that issue - the person responsible for addressing it.
5 | Give the issue a current Red, Red/Amber, Amber/Green or Green rating. This will need to be updated as you take action to address the issue.
6 | State what MITIGATING ACTION is being taken to deal with that issue and its impact on the project.
Changes Log
Changes to the project can affect the benefits that are ultimately experienced by the Users.
It is therefore important to record any changes that are made to the project as it progresses and to involve the Users in these changes.
1 | Enter the PROJECT TITLE to the top of the Spreadsheet.
2 | Enter the DATE that the change was made.
3 | Identify WHO approved the change. Normally this should be the Sponsor or the Project Board.
4 | Detail WHAT the change was that was made.
5 | Detail what the IMPACT on the project will be. This could be positive it will come in under-budget, or negative it will only do 1/2 of what was expected.
Learning Log
It is important to record learnings experienced during a project.
These can be reported in the End of Project Review and used to support future projects.
Learning identified early in the project may also influence the delivery of later stages of the project.
1 | Enter the PROJECT TITLE to the top of the Spreadsheet.
2 | Enter the DATE that learning log entry was made.
3 | Identify WHO recorded that learning.
4 | Provide a brief TITLE for that point of learning.
5 | Explain, in an appropriate level of detail WHAT was learn and how it might IMPACT future projects or stages of this project.
Dependencies Log
This form is used to record other projects, events, activity or areas of work that are linked to your project in a dependant way.
This could be things that are dependent on and could be influenced by an element of your project or things which could influence your project or that your project is dependent on.
1 | Enter the PROJECT TITLE to the top of the Spreadsheet.
2 | Use the drop down menu to record the DIRECTION of the dependency.
Is this something your project is dependent upon, or something which is dependent on your project?
3 | Give a NAME to the dependency item being recorded.
4 | Identify the NATURE of the dependency.
5 | Idenifty the IMPACT of this dependency on your project.
Sheets within this spreadsheet have been ‘Protected’ to restrict the accidental damaging of formulas and formatting within the template.
The password to unlock this is ‘1234’. (Click 'Review', then 'Unprotect Sheet')
Please do feel free to adjust the template as necessary to meet the needs of your project.

## Issues Log
G
Issues Log |  |  |  |  | A/G
PROJECT TITLE |  |  |  |  | A/R
Use this form to record significant issues relating to the project currently being mitigated. |  |  |  |  | R
Key currnet risks (from the Risk Register) and issues (from the Issues Log) should be reported to the board using the Project Highlight report.
ISSUES LOG
Issue Description | Impact on Project | Owner | Current RAG | Mitigating Action
Describe the issue | Describe the impact on the project. | Who is owning the resolution of the issue? |  | What action is planned or being taken, or has been taken to resolve the issue?
The supplier of the windows does not have the stock we need. | There will be a delay to the project and a knock on impact on all other trades | ABC | R | Swiftly looking for a new supplier

## Changes Log
Changes Log
PROJECT TITLE
Use this form to record significant changes that were made to the project during its lifespan.
These changes should represent significant changes to the brief, the propsed outcomes or the intended benefits.
These changes should be reported to the board using the Project Highlight report
Date: | Change approved by: | What change was made? | What will the impact be?
When is this being recorded? | Who approved the change or was consulted regarding the change? | Provide information about what was changed. Was it a change to the focus, the approach, the timescale or the vision for the project? | Provide information about the impact of that change. Will the change have a financial, time, resource, outcome or other impact on the project?
2019-01-01 | John Brown | Following feedback from the stakeholder survey we have decided that the event will be a two-day event rather than a single day event. | The cost has doubled and the programme will be extended - this will require more speakers. The team has adapted to this new brief.

## Learning Log
Learning Log
PROJECT TITLE
Use this form to record learning captured from the project
Key points of learning should be reported to the board using the Project Highlight report
At the end of the project, key learning points can be highlighted within the End of Project Review Form
Date: | Learning recored by: | Point of learning TITLE/SUMMARY: | What was learnt?
When is this being recorded? | Who is recording the learning? | Provide a biref title or summary of the point of learning you are recording | How will the learning influence future practice? Who could the learning be shared with?
2019-01-01 | John Brown | Involving the users in the initial briefing is really important | We held a consultation meeting and involved the users of the project in that conversation. This was really helpful and worked much better than the last time we ran a project like this. We will make sure we do this again.

## Dependencies Log
Influenced by this project
Dependencies Log |  |  |  | An influence on this project
PROJECT TITLE |  |  |  | N/A
Use this form to record other projects, events, activity or areas of work that are linked to your project in a dependant way.
This could be things that are dependent on and could be influenced by an element of your project or things which could influence your project or that your project is dependent on.
Dependancy direction: | Name of dependant: | Nature of dependancy | Impact on the project:
Drop down menu choice |  |  | What are the possible ways that this could impact the project, positively or negatively.
Influenced by this project | The Discipleship course | Will only run after this project has run the evangelistic course. | Project leadership must ensure that the evangelisitic course runs on time so that the advertising for the discipleship course is correct.
An influence on this project | AB Architects | Limited capacity at practice for major projects like this. | Possible delay to our plans being produced causing knock on delay to project timeline.