## Guidance Notes
Risk Regisster
This template has been produced by the Diocese of Bristol as part of its Project Planning Guide
Use this spreadsheet to record any risks identified for your project and to consider how you might mitigate against these.
1 | Begin by reviewing the Risk assessment guidelines and refer to this as you complete the spreadsheet.
2 | Enter the PROJECT TITLE to the top of the spreadsheet.
3 | At the top of the spreadsheet choose a RISK APPETITE level for each category of risk.
4 | For each identified risk complete the RISK DESCRIPTION.
5 | Explain what the IMPACT would be if this risk occurred.
6 | Explain the steps you will take to MITIGATE this risk from occuring and negatively impacting your project.
7 | State who will OWN that risk and be responsible for monitoring it and ensuring that the mitigating actions are carried out.
8 | Enter an IMPACT score for each category of risk for each identified risk.
This should be your assessment of what the IMPACT would be should this risk occur.
9 | Enter a LIKLIHOOD score for each category of risk for each identified risk.
This should be your assessment of how likely it is that this risk should occur.
10 | Having assessed each risk, where appropriate consider what ACTION you might take to improve the assessed situation.
11 | Explain what the ACTION will be.
12 | Identify who will OWN that action to ensure it happens.
13 | Identify a DATE by which that action should take place.
14 | For review and monitoring purposes choose from the drop down menu how ON TRACK that action is.
Sheets within this spreadsheet have been ‘Protected’ to restrict the accidental damaging of formulas and formatting within the template.
The password to unlock this is ‘1234’. (Click 'Review', then 'Unprotect Sheet')
Please do feel free to adjust the template as necessary to meet the needs of your project.

## Risk assessment guidelines
Impact area | 1 | 2 | 3 | 4 | 5
Financial | Less than 3% of allocated budget. | Between 3% - 5% of allocated budget. | Between 5% and 7% of allocated budget. | Between 7% and 10% of allocated budget. | Greater than 10% of allocated budget.
Reputation | Has no negative impact on the organisationss reputation; no media interest. | Minor damages in a limited area. May have localised, low level negative impact on the organisation's reputation / generates low level of complaints. | Minor damages but widespread. Significant localised low level negative impact on the organisation's reputation / generates limited complaints. | High negative impact on the organisation's reputation. Generates significant number of complaints. | Significant and irreparable damage to reputation. Sustained negative publicity resulting in loss of confidence in the organisation.
Engagement | Short term loss of morale with poor performance of non-critical activities. | Minor disengagement. Effectiveness / Efficiency compromised with failures in non-critical activities. | Effectiveness / efficiency compromised in some critical activities. | Failures within some critical activities. | Serious failings across most activities.
Operational | Has no impact on the day to day operation of the organisation. | Low level processes would need to be revised but the matter could be resolved. | A significant amount of work would be required to repair operational systems. | A significant amount of work would need to be done to resolve the matter. | Fundamental organisational changes would need to be implemented.
| Less than 1 months delay in delivery of projects. | Delay of 1-3 months in the delivery of projects. | Delay of 3-6 months in delivery of projects. | Delay of 6-12 months delivery on projects. | Delay of 1 year+ in delivery of projects.
| Little impact on the organisational strategy. | May have an impact on achieving organisational strategy but this could be resolved. | Would impact on the organisational strategic objectives. | Would require a significant shift from organisational strategy. | Would require a fundamental change in organisational strategic objectives.
Liklihood Criteria | 1 | 2 | 3 | 4 | 5
% | <5% | 5 – 20% | 21 – 50% | 51 – 75% | >75%
Liklihood level | Very Low likelihood the risk will occur | Low likelihood the risk will occur | Medium likelihood the risk will occur | High likelihood the risk will occur | Very High likelihood the risk will occur
Frequency of occurance | Risk would occur less than once in 25 years | Risk would occur between once in 25 years or up to once in 5 years | Risk would occur between once in 5 years to just less than once a year | Risk would occur between 1 and 5 times a year | Risk would occur 5 times a year or more
Risk Appetite | Adverse |  | Cautious |  | Open
Financial | In the pursuit of objectives, the organisation will only accept risks which do not result in any financial loss. |  | In the pursuit of objectives the organisation is willing to accept, in some circumstances, risks that may result in some financial loss. |  | In the pursuit of objectives the organisation is willing to accept opportunities that have a high inherent risk and may result may result in significant financial gain or loss.
Reputation and Engagement | The organisation wants to be well respected within the community. It will not accept any negative impact on reputation with any of its key stakeholders and will only tolerate minimum exposure. |  | The organisation wants to be well respected within the community. It will only tolerate low to moderate exposure that may result in negative impact on reputation and stakeholder relationships and is easily recoverable. |  | The organisation wants to be well respected within the community and is willing to accept extensive and prolonged negative exposure to support high risk plans.
Operational | The organisation does not expect any negative impact on operationals. |  | The organisation will only tolerate activity with a low to moderate impact on operations. |  | The organisation is willing to accept a moderate to high level of impact on operations.

## Risk register
Project Risk register
PROJECT TITLE | [10 empty] | Select level
Use this form to record the assess the risks your project faces. |  |  | RISK APPETITE LEVELS |  |  |  |  | Risk score refers to current position |  |  | Adverse | 5
Key current risks should be reported to the board using the Project Highlight report. |  |  | F: Finance | Select level | 0 | [5 empty] | Cautious | 6
|  |  | R: Reputation | Select level | 0 | [5 empty] | Open | 7
Last updated: |  |  | E: Engagement | Select level | 0
Updated by: |  |  | O: Operations | Select level | 0
Risk ID. | Risk description | Impact | Mitigation | Owner | Impact |  | Likeli-hood | Risk score | Above appetite? | Improvement actions
[5 empty] | Group | Score |  |  |  | Action | Owner | Due Date | Status
1 |  |  |  |  | F |  |  | 0 | [6 empty] | <Formula for adverse risk appetite
[5 empty] | R |  |  | 0 | [5 empty] | 6 | <Conditional formatting for adverse risk appetite
[5 empty] | E |  |  | 0 | [6 empty] | <Conditional formatting for status
[5 empty] | O |  |  | 0
2 |  |  |  |  | F |  |  | 0 | [5 empty] | On track | <Status codes
[5 empty] | R |  |  | 0 | [5 empty] | At risk
[5 empty] | E |  |  | 0 | [5 empty] | Completed
[5 empty] | O |  |  | 0 | [5 empty] | Overdue
3 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
4 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
5 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
6 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
7 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
8 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
9 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
10 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
11 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
12 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
13 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
14 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0
15 |  |  |  |  | F |  |  | 0
[5 empty] | R |  |  | 0
[5 empty] | E |  |  | 0
[5 empty] | O |  |  | 0